## Blank
Define
Team Formation & Leadership (Define the team) |  |  |  | Problem definition (Define the project need) |  |  |  |  | Scope (Define what is in and out of scope)
Project Title: | [8 empty] | In Scope: Out of scope:
Area of business:
Project Team Leader/Members | Role
Key risks (see RAID for full details)
AS IS Process Map/SIPOC (Define the process) | [8 empty] | Stakeholder Analysis
[9 empty] | Influence / Power of stakeholders | Meet their needs | Key Player
[10 empty] | Least important | Show consideration
Interest of stakeholders
VOC and CTQ Tree | [8 empty] | Related Documentation References (Where applicable)
Project Charter Ref:
Gantt Chart Ref:
Process Need | [8 empty] | Communications plan Ref:
RACI Ref:
RAID log Ref:
Coaching log Ref:
Secondary KPI
Measure & Analyse
Identify significant factors (Fishbone & 5Why) | [8 empty] | Measurement System Analysis
Baseline process behaviour and stability | [6 empty] | Baseline process capability
Data Note: Explain the patterns trends, common or special cause variation | [6 empty] | Data Note: Explain any investigated outliers
Data Collection Plan | [8 empty] | Related Documentation References (Where applicable)
What | Where | When |  | How often / Frequency | Who |  | Recording method | Status | Data Collection log Ref:
1 | [8 empty] | Additional Data Charts Ref:
2 | [8 empty] | 5 Whys Ref:
3
4
5
6
7
8
9
Improve & Control
Improvement / Implementation Actions | [6 empty] | Benefits realisation
Action |  |  | Responsible |  | Due Date | RAG
Updated Process map (the new way of working) | [6 empty] | Control Plan (see details in referenced documents)
Post Implementation process stability | [6 empty] | Improved process capability
Data Note: Explain the patterns trends, common or special cause variation
Brief desription of methods to validate measurement system used to collect Y and Xs data, gage %R&R and %P/T or other measurement of error, as well as any corrective actions put in place before actual data collection.
Type Effect here (Problem or goal)
Measure
People
Enviroment
Material
Method
Machine
Text here...

## Example
Define
Team Formation & Leadership (Define the team) |  |  |  | Problem definition (Define the project need) | [5 empty] | Scope (Define what is in and out of scope)
Project Title: | [9 empty] | In Scope: Out of scope:
Area of business:
Project Team Leader/Members | Role
Person 1 | Champion
Person 2 | Sponsor
Person 3 | Team Leader
Person 4 | Team member
Person 5 | Team member | [8 empty] | Key risks (see RAID for full details)
AS IS Process Map/SIPOC (Define the process) | [9 empty] | Stakeholder Analysis
[10 empty] | Influence / Power of stakeholders | Meet their needs | Key Player
[11 empty] | Least important | Show consideration
Interest of stakeholders
VOC and CTQ Tree | [9 empty] | Related Documentation References (Where applicable)
| Customer driver 1 |  | CTQ definition |  |  |  |  | Target / Spec limit |  | Project Charter Ref:
Gantt Chart Ref:
Process Need | Customer driver 2 |  | CTQ definition |  |  |  |  | Target / Spec limit |  | Communications plan Ref:
RACI Ref:
| Customer driver 3 |  | CTQ definition |  |  |  |  | Target / Spec limit |  | RAID log Ref:
Coaching log Ref:
| KPI 4 |  | KPI definition |  |  |  |  | Target / Spec limit
Secondary KPI
| KPI 5 |  | KPI definition |  |  |  |  | Target / Spec limit
Measure & Analyse
Identify significant factors (Fishbone & 5Why) | [9 empty] | Measurement System Analysis
Baseline process behaviour and stability | [6 empty] | Baseline process capability
Data Note: Explain the patterns trends, common or special cause variation | [6 empty] | Data Note: Explain any investigated outliers
Data Collection Plan | [9 empty] | Related Documentation References (Where applicable)
What | Where | When |  | How often / Frequency | Who |  | Recording method |  | Status | Data Collection log Ref:
Packs per minute | G&G line | 2021-07-07 |  | 30 packs per hour | Ash Stuart |  | Machine sensor |  | Complete | Additional Data Charts Ref:
2 | [9 empty] | 5 Whys Ref:
3
4
5
6
7
8
9
Improve & Control
Improvement / Implementation Actions | [6 empty] | Benefits realisation
Action |  |  | Responsible |  | Due Date | RAG
Train software out to operatives |  |  | Daniel Croft |  | 2021-06-16
Implement new software on the line |  |  | Frank Fakeman |  | 2021-07-20
Updated Process map (the new way of working) | [6 empty] | Control Plan (see details in referenced documents)
Post Implementation process stability | [6 empty] | Improved process capability
Data Note: Explain the patterns trends, common or special cause variation
Start of process
Process Step
Process Step
Process Step
Process Step
Brief desription of methods to validate measurement system used to collect Y and Xs data, gage %R&R and %P/T or other measurement of error, as well as any corrective actions put in place before actual data collection.
Non value adding
Create a statement defining the problem using 5W1H .E.g.
Who - Who does the problem effect?
What - What is the issue? What is the impact of the issue? What will happen if we don’t solve the problem?
When - When does the problem occur?
Where - Where is the issue occuring?
Why - Why is it important that we fix the problem? What impact it has on the customer, stakeholders etc
How - How are you going to solve the problem (e.g. what method or technique (DMAIC?)) How often does it occur?
A well stated problem statement speeds a robust corrective action process, It helps to identify potential root causes and eliminate bias and noise.Accurate problem statements save time and effort by focusing the team on root cause identification.
Type Effect here (Problem or goal)
Measure
People
Enviroment
Material
Method
Machine
Start of process
Process Step
Process Step
Text here...
Decision
Decision
Process Step